## Executive Summary
Momentra Master Deployment Gap Register
Single deduplicated root-gap register across Personal / Group / Business / Shared Platform
Portfolio Summary | Domain | Total | P0
Total root gaps | Shared Platform
P0 root gaps | Personal
P1 root gaps | Group
P2/P3 root gaps | Business
Open
Deferred
Release logic
• Audit coverage may be 100% while runtime readiness is below 100%. This register tracks deduplicated root causes, not every audit observation.
• P0 = launch/security/data-integrity/core-flow blocker. P1 = required V1 incomplete/incorrect. P2/P3 = non-blocking/deferred/cleanup.
• Close dependencies first. A domain row is not CLOSED until its stated exit evidence exists; code completion alone is insufficient.
• Shared Platform root gaps are dependencies for multiple domain gaps and should not be duplicated inside each domain.

## Master Gap Register
Gap ID | Domain | Module / Surface | Root Gap | Gap Type | Severity | Status | Current / Evidence | Required Closure | Exit / Validation Evidence | Audit Areas | Depends On | Execution Order | Execution Wave | Source Basis
SP-001 | Shared Platform | API Contracts | OpenAPI vs live router reconciliation | CONTRACT_GAP | P1 | OPEN | OpenAPI materially understates mounted routes; contract inventory and runtime are not one authoritative set. | Reconcile OpenAPI, endpoint inventory, router and service implementation; classify documented-only, undocumented-live, duplicate, deprecated. | All active V1 endpoints have one authoritative contract; zero unknown live routes. | 03 |  | 1 | Foundation | api_middleware_sql_audit_e6cb162f.plan (1).md
SP-002 | Shared Platform | API Standards | Idempotency / OCC / stable errors | CONTRACT_GAP | P0 | OPEN | Cross-cutting command guarantees are not proven consistently. | Enforce Idempotency-Key, optimistic concurrency/version semantics, authorization and stable error shapes across all mutating V1 commands. | Retry, conflict, unauthorized and validation contract suites pass. | 03,11,15,16 | SP-001 | 2 | Foundation | Business Deployment Closure Pack CL-40; 16-area audit
SP-003 | Shared Platform | Identity & Authorization | Service-role + RLS authorization model | AUTH_GAP | P0 | OPEN | RLS exists, but application uses privileged/service-role patterns; product authorization must be proven independently. | Define and enforce application identity/context propagation; negative-test Personal ownership, Group membership/roles and Business company/team/location scope. | Cross-tenant/group/company leakage tests all pass; no client-trusted authorization. | 11 | SP-002 | 3 | Security | 16-area audit Area 11
SP-004 | Shared Platform | Governance | RBAC / policy enforcement | AUTH_GAP | P0 | OPEN | Governance/role policy data exists but runtime enforcement is not fully proven. | Reconcile frozen role/permission/policy matrices with server-side governance resolver and command authorization. | Every governed action has server-side permission proof and forbidden-path tests. | 11,12 | SP-003 | 4 | Security | Group GM0-G03/GM0-G05; audit Area 11
SP-005 | Shared Platform | Migrations | Fresh + upgrade migration certification | SCHEMA_GAP | P0 | OPEN | Production readiness requires clean install and forward upgrade validation through latest migrations. | Run migration chain on clean PostgreSQL/Dev Supabase and supported upgrade baseline; validate constraints, indexes, enums, RLS, seeds. | Fresh and upgrade paths complete with schema diff = expected and no ordering failures. | 06 | SP-003 | 5 | Data Foundation | 16-area audit Area 6
SP-006 | Shared Platform | Data Ownership | Canonical ownership registry | DATA_GAP | P0 | OPEN | Closest-writer/generic persistence exists in some flows; single authoritative owner per durable fact must be enforced. | Freeze durable fact -> canonical table/entity -> writer command ownership; prohibit generic escape writers where first-class fact exists. | Zero durable V1 fact has competing canonical owners or client-side authority. | 05 | SP-005 | 6 | Data Foundation | Audit Area 5; Business source/decision rules
SP-007 | Shared Platform | Table Utilization | 200-table classification | DATA_GAP | P1 | OPEN | Apparently unused tables include canonical/projection/worker/future/legacy possibilities; no-rest != orphan. | Classify every table CANONICAL/PROJECTION/WORKER/FUTURE/LEGACY/ORPHAN and document expected writer/reader. | Every table classified; orphan deletion candidates separately approved. | 07 | SP-005,SP-006 | 7 | Data Foundation | 16-area audit Area 7
SP-008 | Shared Platform | Events & Workers | Outbox / retry / DLQ / checkpoint chain | WORKER_GAP | P0 | OPEN | Post-write worker reliability and recovery are not fully proven for all commands. | Certify command transaction -> outbox -> dispatcher -> worker -> retry/DLQ/checkpoint with idempotent recovery. | Representative failure/retry/recovery tests pass and no committed write is silently lost. | 09 | SP-002,SP-005,SP-006 | 8 | Runtime Core | 16-area audit Area 9
SP-009 | Shared Platform | Projections | Projection generation and persistence | PROJECTION_GAP | P0 | OPEN | Projection tables/read models are sometimes bypassed by inline queries; authoritative derivation path is inconsistent. | For each frozen projection define canonical sources, generator, persistence/cache, version/freshness and API read contract. | Pulse/Life/Memory/Finance read models are reproducible and projection lineage is documented. | 08 | SP-008 | 9 | Runtime Core | 16-area audit Area 8
SP-010 | Shared Platform | Refresh | Write -> invalidate -> refetch | REFRESH_GAP | P0 | OPEN | Realtime clients are incomplete and authoritative post-write refresh is not universally proven. | Standardize invalidation semantics: canonical write -> event -> projection -> FCM/SSE/cache invalidation -> authoritative refetch. | E2E tests show successful writes reach visible UI without stale authoritative state. | 13 | SP-008,SP-009 | 10 | Runtime Core | Audit Area 13; Business Life refresh rule
SP-011 | Shared Platform | Metrics | Metric catalogue + golden vectors | METRIC_GAP | P0 | OPEN | Some formulas/thresholds/windows remain draft or use heuristics/proxies. | Freeze metric version, inputs, window, formula, thresholds/state mapping and golden fixtures for all V1 metrics. | All deterministic V1 metrics pass golden tests and reconcile to canonical data. | 10 | SP-006,SP-009 | 11 | Intelligence Core | Audit Area 10; Group GM0-G04
SP-012 | Shared Platform | State Machines | Lifecycle transition certification | BUSINESS_RULE_GAP | P1 | OPEN | Polls, approvals, invites, issues/risks, goals, shares and recurring objects require allowed/forbidden transition proof. | Define transition matrices and enforce server-side state/permission/audit rules. | Allowed and prohibited transitions pass integration tests with audit evidence. | 12 | SP-002,SP-004,SP-006 | 12 | Runtime Core | 16-area audit Area 12
SP-013 | Shared Platform | Mobile Parity | iOS / Android capability parity | CLIENT_GAP | P1 | OPEN | Known endpoint and realtime capability asymmetries exist across clients. | Reconcile frozen V1 capabilities and DTO/API wrappers as BOTH/IOS_ONLY/ANDROID_ONLY/MISSING; close required parity. | All launch V1 capabilities classified; required items BOTH or explicitly platform-deferred. | 04 | SP-001,SP-002 | 13 | Clients | 16-area audit Area 4
SP-014 | Shared Platform | E2E Certification | 19 moment journeys + backend write proof | TEST_GAP | P0 | OPEN | Audit plan records 0/19 Maestro moment journeys executed and backend write verification pending. | Execute all frozen critical journeys with DB, outbox, projection and UI evidence. | 19/19 required journeys pass or approved launch exclusions are explicit; backend write evidence complete. | 14 | SP-002,SP-003,SP-005,SP-008,SP-009,SP-010,SP-013 | 90 | Certification | 16-area audit preliminary findings
SP-015 | Shared Platform | NFR | Performance / resilience / recovery | PERFORMANCE_GAP | P1 | OPEN | Production latency, query plans, pooling, Redis failure, retries, backups and reconnect behavior require certification. | Run p50/p95/p99 and failure-mode tests on critical paths; validate indexes, pool, rate limits, backup/restore and offline/reconnect. | NFR thresholds satisfied or documented exception approved. | 15 | SP-005,SP-008,SP-009 | 91 | Certification | 16-area audit Area 15
SP-016 | Shared Platform | Observability | Logging / telemetry / alerting / release gate | TEST_GAP | P1 | OPEN | Release observability and automated regression gate must be proven end-to-end. | Verify correlation IDs, structured errors, worker/DLQ/projection alerts and CI contract/integration/auth/migration/E2E gates. | Production release gate is automated: Unknown=0, P0=0, regression green. | 16 | SP-014,SP-015 | 99 | Certification | 16-area audit Area 16
SP-017 | Shared Platform | Legacy Cleanup | Unmounted/deprecated route and schema cleanup | LEGACY | P3 | DEFERRED | Unmounted duplicate router surfaces and legacy artifacts can create ambiguity. | Remove or explicitly quarantine deprecated/unmounted routes and confirmed orphan schema after release stabilization. | No deprecated surface can be accidentally mounted or used by clients. | 03,07 | SP-001,SP-007 | 120 | Post-launch | 16-area audit preliminary findings
SP-018 | Shared Platform | AI / Provenance | Deferred intelligence honesty | DEFERRED | P2 | DEFERRED | AI narrative/pattern/playbook outputs are not universally worker/provenance-backed. | Keep unavailable intelligence honest-empty/feature-flagged until worker, provenance, evidence and confidence contract exists. | No fabricated AI values; deterministic core functions without AI. | 08,09,10 | SP-008,SP-011 | 110 | Deferred | Business and Business Life closure rules
PER-001 | Personal | Personal Core | Forward V035-V037 schema implementation | SCHEMA_GAP | P0 | OPEN | V035-V037 are promoted to implementation baseline but physical deployment remains pending. | Implement/review forward SQL, constraints, indexes and RLS for Personal promoted canonical structures. | Latest schema contains all approved Personal structures and migration tests pass. | 05,06 | SP-005,SP-006 | 20 | Personal Foundation | Personal POST-RESOLUTION Freeze Gate
PER-002 | Personal | Personal Core | Freeze and implement proposed Personal API routes/DTOs | API_GAP | P0 | OPEN | Many Personal mapped interactions remain on proposed routes rather than physically frozen runtime contracts. | Freeze OpenAPI/DTOs and implement routes for Personal moment creation and domain setup/observations/commands. | Every actionable Personal widget has a concrete mounted route or explicit static/deferred classification. | 02,03 | PER-001,SP-001,SP-002 | 21 | Personal Foundation | Personal 1,979 widget mapping; Blocker Register
PER-003 | Personal | Life Operations | Recovery observation/detail runtime | API_GAP | P1 | OPEN | Life Operations recovery widgets map to proposed recovery-observation routes and promoted schema, not proven runtime. | Implement recovery observation/detail command/read contracts and projection refresh. | Recovery capture persists canonically and Pulse/Life/Memory refresh correctly. | 02,08,14 | PER-001,PER-002,SP-008,SP-009,SP-010 | 30 | Personal Vertical | Personal Row Validation Register
PER-004 | Personal | Future Building | D04 Future Building extensions | DATA_GAP | P1 | OPEN | Future Building still has a unique product/data decision family and previously missing canonical fields. | Close D04 against frozen UI; implement canonical fields, commands and reads without inventing alternate storage. | Future Building setup/quick adds/read models have complete traceability and runtime tests. | 01,02,05,10 | PER-001,PER-002,SP-011 | 31 | Personal Vertical | Personal Freeze Gate D04
PER-005 | Personal | Lifestyle | Lifestyle profile/setup persistence | SCHEMA_GAP | P1 | OPEN | Lifestyle setup is design-ready but personal.lifestyle_profile and route/transport are not in earlier physical baseline. | Deploy promoted Lifestyle profile schema and setup route/DTO; validate RLS and refresh. | Lifestyle setup saves/loads all frozen fields and projections update. | 02,05,06,08 | PER-001,PER-002,SP-009,SP-010 | 32 | Personal Vertical | Personal Blocker Register Lifestyle
PER-006 | Personal | Relationships | D05 Relationship profile | DATA_GAP | P1 | OPEN | Relationship profile remains a unique unresolved product/data decision family. | Close D05 and implement frozen profile canonical/API/read contract. | Relationship profile widgets have complete canonical trace and E2E evidence. | 01,02,05 | PER-001,PER-002 | 33 | Personal Vertical | Personal Freeze Gate D05
PER-007 | Personal | Relationships | D06 target/tag/edit matrix | BUSINESS_RULE_GAP | P1 | OPEN | Relationship target/tag/edit semantics remain a unique unresolved decision family. | Freeze editable fields, target/tag semantics, validations and update commands. | Create/edit/target/tag lifecycle tests pass and UI reflects authoritative state. | 01,02,12 | PER-006,SP-012 | 34 | Personal Vertical | Personal Freeze Gate D06
PER-008 | Personal | Personal Analytics | D07 logic/enum/formula catalogue | METRIC_GAP | P0 | OPEN | Personal logic/enums/formulas remain a unique unresolved decision family. | Freeze enum catalogue, derivation formulas, thresholds and versioned metrics; implement server-side. | Personal Pulse/Life/Memory deterministic outputs pass golden fixtures. | 10 | SP-011,PER-001 | 35 | Personal Intelligence | Personal Freeze Gate D07
PER-009 | Personal | Personal Projections | Pulse / Life / Memory projection implementation | PROJECTION_GAP | P0 | OPEN | Personal production is explicitly not final until projection implementation is completed. | Implement/promote Personal read models with freshness/version and refetch semantics. | Personal canonical writes deterministically update Pulse/Life/Memory and visible UI. | 08,13,14 | PER-002,PER-003,PER-004,PER-005,PER-006,PER-008,SP-009,SP-010 | 45 | Personal Integration | Personal Freeze Gate production status
PER-010 | Personal | Personal E2E | Personal V1 vertical certification | TEST_GAP | P0 | OPEN | Frozen UI/interaction mapping exists, but production-final behavior requires runtime proof. | Run Personal creation, setup, Quick Add, edit, Pulse, Life, Memory and Action Center flows with DB/projection evidence. | Personal launch journeys pass with no unknown mappings. | 14 | PER-009,SP-014 | 92 | Certification | 16-area audit Area 14
GRP-001 | Group | Poll Kernel | Shared Poll physical target / transition | SCHEMA_GAP | P0 | OPEN | V001-V030 has collaboration.poll family while freeze requires shared Poll kernel after V032; dual-engine ambiguity is prohibited. | Complete shared Poll physical target and migration; reconcile canonical writer/reader. | One poll canonical path is active; no silent dual-engine persistence. | 05,06,12 | SP-005,SP-006 | 20 | Group Foundation | GM0-G01
GRP-002 | Group | Group Analytics | Production metric semantics | METRIC_GAP | P0 | OPEN | Metric versions/formulas/thresholds remain draft in Group release status. | Freeze Group metric catalogue and implement deterministic analytics/projection calculations. | Group KPI golden vectors pass and client displays server-authoritative values. | 10 | SP-011,GRP-001 | 25 | Group Foundation | GM0-G04
GRP-003 | Group | Group Governance | Policy / approval threshold semantics | BUSINESS_RULE_GAP | P0 | OPEN | Policy versions/rules/approval thresholds remain draft. | Freeze server governance policy catalogue and bind approval/eligibility rules to it. | No governed Group action relies on hardcoded UI eligibility; transition tests pass. | 11,12 | SP-004,SP-012 | 26 | Group Foundation | GM0-G05
GRP-004 | Group | Quick Add | Subtype capability reconciliation | CLIENT_GAP | P1 | OPEN | Final per-Moment-Type Quick Add subsets must be reconciled to the frozen 4,210-widget authority. | Reconcile each Group moment type Quick Add capability with frozen mapping and runtime enablement. | No enabled unsupported action and no frozen required action omitted. | 01,02,04 | GRP-002,GRP-003,SP-013 | 30 | Group Vertical | GM0-G02
GRP-005 | Group | Roles & Permissions | Frozen role/permission reconciliation | AUTH_GAP | P1 | OPEN | Current role/permission matrix may differ from frozen governance authority; action widgets remain partial until confirmed. | Map every action widget to permission code/path and enforce server-side. | Positive/negative role tests pass for all governed Group commands. | 11 | GRP-003,SP-003,SP-004 | 31 | Group Vertical | GM0-G03
GRP-006 | Group | Collaboration Quick Adds | Explicit command routes/DTOs | API_GAP | P0 | OPEN | Canonical tables exist for booking/vendor/attendance/planning/update/purchase/living actions but explicit command contracts are incomplete. | Freeze and implement explicit /v1 routes and DTOs for collaboration quick adds; remove generic fallbacks. | Each frozen Quick Add lands in intended canonical fact and refreshes projections. | 02,03,05,14 | GRP-001,GRP-003,SP-001,SP-002,SP-006,SP-008 | 32 | Group Vertical | GM0-G06
GRP-007 | Group | Settlement | Settlement HTTP contract | API_GAP | P0 | OPEN | Finance settlement canonicals exist and UI has a multi-screen settlement flow, but explicit endpoint is a contract gap. | Freeze settlement commands/read DTOs with server-side validation and authorization. | Settlement E2E creates valid allocations/obligations and refreshes Finance/Life. | 02,03,12,14 | GRP-005,SP-002,SP-006,SP-008 | 33 | Group Vertical | GM0-G07
GRP-008 | Group | Group Projections | Widget-level projection contract granularity | PROJECTION_GAP | P1 | OPEN | group_* projections may use payload blobs while exact widget-specific payload contract is unspecified for partial rows. | Freeze projection DTO/payload schemas for Pulse/Life/Memory/Finance/recent activity and bind clients. | All read widgets have exact projection fields and freshness/refetch semantics. | 08,13 | GRP-002,GRP-006,GRP-007,SP-009,SP-010 | 45 | Group Integration | GM0-G08
GRP-009 | Group | Runtime Engine | Production engine execution | TEST_GAP | P0 | OPEN | Release status states V001-V030 were not executed end-to-end on clean PostgreSQL/Dev Supabase. | Execute full Group schema/runtime engine and verify writes, workers, projections and reads. | Clean environment Group deployment and critical E2E suite pass. | 06,09,14 | GRP-001,GRP-006,GRP-007,GRP-008,SP-014 | 93 | Certification | GM0-G09
BUS-001 | Business | Team Operations | Explicit Decision / Meeting / Retrospective / Activity commands | API_GAP | P0 | OPEN | These Quick Adds currently use generic business-updates closest writer. | Implement first-class commands and canonical work/business facts; rewire clients. | Each action persists intended canonical fact, emits outbox and refreshes projections. | 02,03,05,09,14 | SP-002,SP-006,SP-008 | 30 | Business Vertical | Business Closure rows 7-10 / CL-13
BUS-002 | Business | Team Operations | Recognition canonical contract | SCHEMA_GAP | P0 | OPEN | Recognition currently uses generic business-update and requires canonical schema/API. | Create business.recognition and first-class command; rewire client. | Recipient/type/message persist canonically and appear in downstream reads. | 02,03,05,06,14 | SP-005,SP-006,SP-008 | 31 | Business Vertical | Business Closure row 11 / CL-14
BUS-003 | Business | Team Operations | Milestone client rewire | CLIENT_GAP | P0 | OPEN | First-class milestone route exists but client uses closest-writer fallback. | Wire frozen Milestone sheet to milestone endpoint and remove fallback. | Milestone row created with no business_update write. | 02,04,14 | SP-013,SP-002 | 32 | Business Vertical | Business Closure row 12 / CL-16
BUS-004 | Business | Team Operations | Blocker vs Risk semantics | BUSINESS_RULE_GAP | P1 | OPEN | Issue route exists; Risk Flag semantics may require canonical risk rather than issue. | Validate UI semantic selection and route risk actions to canonical risk command. | Risk Flag creates risk when risk semantics selected; blocker remains issue. | 05,12 | SP-006,SP-012 | 33 | Business Vertical | Business Closure row 13 / CL-13
BUS-005 | Business | Team Operations | Business poll participant/anonymity validation | AUTH_GAP | P1 | OPEN | Poll is first-class but Group-style membership assumptions may fail in Business participant scope. | Validate company/team participant scope, anonymity and read DTO authorization. | Authorized Business participants vote/read correctly; unauthorized cannot. | 11,12 | SP-003,SP-004,SP-012 | 34 | Business Vertical | Business Closure row 14 / CL-17
BUS-006 | Business | Team Operations | Capacity / workload metrics | METRIC_GAP | P1 | OPEN | Capacity and workload Pulse values are missing/honest-empty. | Implement team_capacity_utilization_v1 and rolling workload-by-department metrics; bind Pulse DTO. | Golden metric tests pass and non-empty values reconcile to assignments/capacity. | 08,10 | SP-009,SP-011 | 40 | Business Reads | Business Closure rows 0-1 / CL-12
BUS-007 | Business | Team Operations | Roster / share / weekly report | API_GAP | P1 | OPEN | Recipient roster missing, share is no-op/disabled, weekly report CTA is miswired. | Implement membership read, audited share/notify command and weekly report projection/read; wire clients. | Roster scoped correctly, share audited/delivered, report CTA opens reconciled data. | 02,03,08,11,14 | SP-003,SP-009,SP-013 | 41 | Business Reads | Business Closure rows 3,5,6 / CL-11,CL-40
BUS-008 | Business | Business Runway | Runway deltas / progress snapshot metrics | METRIC_GAP | P1 | OPEN | MoM/trend deltas unbound and progress snapshot uses missing/heuristic values. | Implement comparison windows, collections/health metrics and bind runway Pulse DTO. | Golden previous-period tests pass and snapshot reconciles to invoices/cash/burn. | 08,10 | SP-009,SP-011 | 42 | Business Reads | Business Closure rows 15-16 / CL-25,CL-37
BUS-009 | Business | Business Runway | Tax obligation first-class fact | SCHEMA_GAP | P0 | OPEN | Tax Entry is persisted as expense category TAX, conflating obligation with payment fact. | Implement finance.tax_obligation and company tax-obligation command; expense remains payment only. | Tax type/period/due/status persist independently and reconcile to payments. | 02,05,06,14 | SP-005,SP-006 | 35 | Business Vertical | Business Closure row 19 / CL-21
BUS-010 | Business | Business Runway | Investor update first-class contract | SCHEMA_GAP | P0 | OPEN | Investor Update uses generic business-updates. | Implement structured investor update/dispatch with audience and delivery status. | Audience/content/dispatch/audit persist canonically. | 02,05,06,14 | SP-005,SP-006,SP-008 | 36 | Business Vertical | Business Closure row 20 / CL-22
BUS-011 | Business | Business Runway | Budget alert semantics | BUSINESS_RULE_GAP | P0 | OPEN | Budget Alert is persisted as issue/severity rather than budget/metric threshold event. | Implement budget alert contract tied to budget, threshold, period and evidence; issue may be consequence only. | Alert reconciles to budget/metric evidence and downstream notification. | 05,10,12 | SP-006,SP-011,SP-012 | 37 | Business Vertical | Business Closure row 21 / CL-23
BUS-012 | Business | Business Runway | Forecast scenario/lines canonical contract | SCHEMA_GAP | P0 | OPEN | Forecast Update uses generic business-update and lacks versioned scenario/line semantics. | Implement finance.forecast_scenario + forecast_line and company forecast command. | Versioned forecast drives runway projection and versioning tests pass. | 02,05,06,08 | SP-005,SP-006,SP-009 | 38 | Business Vertical | Business Closure row 22 / CL-20
BUS-013 | Business | Business Operations | Budget review canonical semantics | BUSINESS_RULE_GAP | P0 | OPEN | Budget Review uses generic business-update. | Implement budget review against budget/review canonical semantics, tied to period/variance/notes and finance facts. | Review is auditable and reconciles to budget facts. | 02,05,12 | SP-006,SP-012 | 39 | Business Vertical | Business Closure row 27 / CL-23
BUS-014 | Business | Business Operations | Vendor / SLA existing-selection UX | CLIENT_GAP | P1 | OPEN | First-class vendor/SLA routes exist but UX often creates new vendor, risking duplicates. | Rewire UI to select existing vendor/contract/SLA definition before update/check; create only explicitly. | Existing chain can be selected/updated without duplicate vendor creation. | 01,02,04 | SP-013,SP-002 | 43 | Business UX | Business Closure rows 28-29 / CL-27,CL-28
BUS-015 | Business | Business Operations | Issue evidence persistence | API_GAP | P1 | OPEN | Issue exists first-class but evidence/attachment affordance is UI-only. | Bind evidence to supported media/evidence contract or remove affordance until contract exists. | Authorized evidence reference persists and renders. | 02,03,05,11 | SP-003,SP-006 | 44 | Business UX | Business Closure row 30 / CL-26,CL-40
BUS-016 | Business | Business Operations | Reminder / escalation + share commands | API_GAP | P1 | OPEN | Escalate/send reminder labels and Memory Share lack complete audited delivery behavior. | Implement notification/governance commands and audited share semantics; otherwise remove actionable affordance. | Authorized action produces audited delivery and stable error behavior. | 02,03,11,12 | SP-002,SP-003,SP-012 | 46 | Business Integration | Business Closure rows 25-26 / CL-40
BUS-017 | Business | Company Life | Company-scoped Life route correction | API_GAP | P0 | OPEN | Runtime uses moment-scoped Life semantics; finalized design requires company-scoped B-L01. | Move Business Life to GET /v1/companies/{companyId}/life; prohibit removed family/moment Life routes; enforce company auth. | Only company route serves B-L01; cross-company negative tests pass. | 02,03,11,14 | SP-001,SP-003 | 47 | Business Life | Business Life LIFE-01,LIFE-14,LIFE-16
BUS-018 | Business | Company Life | Versioned DTO / module cards / activity / freshness | PROJECTION_GAP | P0 | OPEN | Life payload is thin/proxy; core module cards, activity and freshness/version are incomplete. | Implement versioned Company Life DTO/projection with module cards, company activity, projectionVersion/updatedAt/status. | Core cards/activity are server-authoritative and projection-consistent. | 08,13 | BUS-017,SP-009,SP-010 | 48 | Business Life | Business Life Wave 1 / LIFE-02,04,05,06,09,15
BUS-019 | Business | Company Life | business_life_health_v1 + signals | METRIC_GAP | P0 | OPEN | Health/signal values use proxy/thin semantics rather than frozen deterministic metric and evidence taxonomy. | Implement business_life_health_v1 plus signal taxonomy/ranking/evidence on server. | Golden health/signal tests pass; no client proxy calculations. | 10 | BUS-018,SP-011 | 49 | Business Life | Business Life Wave 2 / LIFE-03,LIFE-08
BUS-020 | Business | Company Life | Trends / journey / vendor support | PROJECTION_GAP | P1 | OPEN | Six-month trends, journey inclusion and vendor supporting payload semantics require deterministic closure. | Implement versioned trend series, journey rules/order and vendor supporting payload. | Trends/journey reconcile to canonical history; vendor payload does not alter v1 health unexpectedly. | 08,10 | BUS-018,BUS-019 | 50 | Business Life | Business Life Wave 3 / LIFE-07,10,11
BUS-021 | Business | Company Life | Share + detailed report | API_GAP | P1 | OPEN | Company Life Share and Detailed Report actions are not fully implemented/wired. | Implement authorized/audited share and report read tied to same Life snapshot/version. | Share is auditable/idempotent; report reconciles to Life snapshot. | 02,03,11,14 | BUS-018,SP-003,SP-002 | 51 | Business Life | Business Life Wave 4 / LIFE-12,LIFE-13
BUS-022 | Business | Business Integration | Business write -> outbox -> projection -> refetch | REFRESH_GAP | P0 | OPEN | Business closure pack explicitly requires proof for all remediated writers. | For every Business P0/P1 writer prove canonical write, outbox event, projection update and client refetch. | No successful Business write leaves stale canonical UI. | 09,13,14 | BUS-001,BUS-002,BUS-003,BUS-009,BUS-010,BUS-011,BUS-012,BUS-013,BUS-017,BUS-018,SP-008,SP-009,SP-010 | 60 | Business Integration | Business Closure row 33 / CL-13,CL-40
BUS-023 | Business | Business E2E | Business release-blocker certification | TEST_GAP | P0 | OPEN | Business packs require every P0/P1 blocker closed with validation evidence. | Execute contract/integration/auth/metric/projection/mobile E2E validations for Team Ops, Runway, Operations and Company Life. | All Business P0/P1 blocker rows CLOSED with evidence; deferred AI remains honest-empty. | 14,16 | BUS-022,BUS-006,BUS-007,BUS-008,BUS-014,BUS-015,BUS-016,BUS-019,BUS-020,BUS-021,SP-014 | 95 | Certification | Business Closure Packs release rule

## Execution Sequence
Wave | Order Range | Focus | Primary Gaps | Entry Dependency | Exit Gate
Wave 0 | 1-7 | Contract, security, migrations, canonical ownership | SP-001..SP-007 | None | Authoritative API/security/schema/ownership baseline established.
Wave 1 | 8-13 | Events, projections, refresh, metrics, state, client parity | SP-008..SP-013 | Wave 0 | Shared runtime rails are reliable and deterministic.
Wave 2 | 20-29 | Domain foundations | PER-001/002/008; GRP-001/002/003; Business canonical foundations | Waves 0-1 | Required schema/API/governance/metric foundations exist.
Wave 3 | 30-44 | Domain vertical commands + reads | Personal domain setup; Group Quick Adds/settlement; Business Team Ops/Runway/Ops | Wave 2 | Each domain command lands in correct canonical fact and reads are bound.
Wave 4 | 45-60 | Projection + Life + integration closure | PER-009; GRP-008; BUS-017..022 | Waves 1-3 | Write -> outbox -> projection -> refetch works across domains.
Wave 5 | 90-99 | Certification / production gate | SP-014..016; PER-010; GRP-009; BUS-023 | All release-blocking dependencies | P0=0; P1 blockers=0 for launch scope; regression and NFR gates green.
Deferred | 110+ | AI provenance + legacy cleanup | SP-018, SP-017 | Core launch complete | No fabricated intelligence; cleanup isolated from launch risk.

## Dependency Map
Dependency Layer | Must Close Before | Why
SP-001 API contract truth | SP-002, PER-002, GRP-006/007, BUS API rows | Implementation cannot be certified against drifting contracts.
SP-003/004 authorization/governance | Group/Business governed commands; Company Life | Scope and role correctness must exist before E2E sign-off.
SP-005/006 migrations + canonical ownership | All domain writers | Do not wire clients to non-existent or noncanonical persistence.
SP-008 events/workers | SP-009/010 projections/refresh; domain integration | Projection freshness depends on reliable event propagation.
SP-011 metric catalogue | Personal D07, Group analytics, Business Pulse/Life | UI values must be server-authoritative and testable.
SP-013 parity | Domain mobile E2E | Both launch clients must call same frozen contracts.
Domain command closure | Domain projection/Life closure | Read models cannot be trusted until writes land canonically.
Projection + refresh closure | SP-014 / domain certification | Visible product behavior is the final proof, not API success alone.

## Source Index
Source | Use in Register
api_middleware_sql_audit_e6cb162f.plan (1).md | 16-area audit scope, preliminary cross-stack findings and certification gates.
Momentra_Personal_1979_Widget_FINAL_PreFreeze_Validation_v2_Blockers_Resolved.xlsx | Personal 66-screen/1,979-widget freeze, V035-V037 implementation baseline, D04-D07 remaining decision families.
Momentra_Group final field-level mapping / GM0 Gap Register | Group 217-screen/4,210-widget authority and GM0-G01..G09 implementation blockers.
Momentra_Business_Deployment_Closure_Pack.xlsx | 34 Business closure rows and canonical execution waves.
Momentra_Business_Life_Deployment_Closure_Pack.xlsx / Plan | 17 Company Life closure rows, company-scoped route, projection/metric/refresh/security rules.
Finalized Architecture / ERD / FRD / DDL / PostgreSQL / API mapping documents | Design authority and canonical ownership baseline referenced by audits and closure packs.

## Legend
Field | Meaning
Root Gap | One deduplicated remediation unit; repeated symptoms across audits map to this row.
Depends On | Gap IDs that should be closed/established before this row can be certified.
Execution Order | Suggested dependency-respecting order; same-range items may execute in parallel.
OPEN | Root cause remains to be implemented and/or validated.
DEFERRED | Explicitly non-blocking for launch if product/release agrees.
Exit / Validation Evidence | Mandatory proof for closure; implementation without evidence is not CLOSED.